| PRODUCED BY |  | REVIEWED BY | APPROVED BY |
| --- | --- | --- | --- |
| Noelia Mendoza |  | Latifi Chelala | Latifi Chelala |
| Historical revisions |  |  |  |
| Version | Date | Modifications |  |
| 00 | 12/16/2020 | Creation |  |
| 01 | 04/15/2021 | Page: All |  |
| 02 | 04/01/2022 | Pages: 1,2,5,8,9,10 |  |

- OBJECTIVES

- Promote local development and promote the close link between the communities and the company.

- Improve the production and innovation capacity to add value to the income-generating activities of indigenous families.

- SCOPE

| Place of Application | Industrial Component: TODirectly Affected Area (ADA), Direct Influence Area (AID). Forest Component: Area of ​​Direct Influence (AID). indigenous communities: Redención, Jeguahaty, Vy'a Renda, Takuarendyju, Takuarita, Sati, Guyra Ñe'engatu Amba, Mberyvo. Yvyty Rovi, Apyka Jegua. |  |
| --- | --- | --- |
| Components | Industrial | Forest |
| stages | Construction and operation | Installation, operation and maintenance |

- DEFINITIONS

- Direct Area of ​​Influence (AID) of the industrial component: [Include 5] districts near the site of the Industrial Plant, including 18 communities that are within a radius of 13 km from the site. These territories are the following: Concepción, [Paso Horqueta], Belén, Horqueta and Loreto, and the communities/localities: L. Petit, Cnel. Mongelós, Jhugua Zarzo, Laguna Plato, Mongelós Pirity, Piquete Cue, Jhugua Gonzalez, Callejón San Luis, Mbocayaty, Callejón San Ramón, San Antonio, Curuzu Ñu, Costa Pucu, Paso Ita, Ko'ê Porâ, Costa Ferreira, Saladillo and Colonia Spring.

- Direct Area of ​​Influence (AID) of the forestry component:It includes 7 districts in which the areas of the project's forest plantations and the main access roads to them are located, including 16 neighboring communities. These territories are the following: Sergeant José Félix López, Paso Barreto, Loreto, San Alfredo, Horqueta and Arroyito in the department of Concepción; the district of Bella Vista Norte of the department of Amambay and its communities/towns: Isla Hermosa (Isla Tuyú), town of Paso Barreto, Colonia Jorge Sebastián Miranda (Jhugua Ñandu), Estribo del Plata, Puentesiño, Laguna Cristo Rey, Anderi, Islería , Virgen del Camino, Jhugua Guasu, Jhugua Po'i, Santísima Trinidad, Paso Mbutu, Calle 15, Dominguez Nigó, and Ayala Cué.

- Directly Affected Area (ADA) of the industrial component:Social units and communities located in the immediate surroundings of the Industrial Plant installation, within a radius of 1 km.[Includes the towns called Piquete Cue and Pyrenda].

- Area of ​​Direct Influence (AID) of the indigenous component:it is made up of the indigenous communities located between 1 and 15 kilometers from the Paracel SA developments and that could be affected by the project. The indigenous communities identified are from the Paĩ Tavyterã and Mbya Guaraní ethnic groups and a multicultural indigenous community made up of indigenous people of different ethnic groups, mainly from the Maskoy language. The identified indigenous communities are: Redención, Jeguahaty, Vy'a Renda, Takuarendyju, Takuarita, Sati, Guyra Ñe'engatu Amba, Mberyvo, Yvyty Rovi, Apyka Jegua.

- RESPONSIBILITIES

| Communications and Social Sustainability Management | Design social intervention strategies framed in this program and lead its implementation. |
| --- | --- |
| All areas of the company | Comply with the provisions of this program (if applicable). |
| General management | Approve budgets corresponding to the program. |

- DEVELOPING

5.1. Related Impact

- Forestry and Industrial Component

- Affectation of the social and community network (family, social and productive).

- Impact on units in the immediate environment due to access or proximity to the plant (industrial component) and small communities near/bordering forest fields and access to them.

- Changes in customs and uses.

- Increased discomfort or calm.

- Affectation of the health and safety of third parties.

- Indigenous Component

- Expansion of sources of income generation in the district.

- Decrease in poverty levels.

- Improvement of conditions for food security.

- Improvement of conditions for access to inputs for agricultural production and commercial inclusion in value chains.

- Increased vocational training opportunities.

5.2. Development of the Proposed Measures

| Associated Population | Proposed Measures | Concrete actions | Indicators | Verification Methods | Linked standards |
| --- | --- | --- | --- | --- | --- |
| ADA and AID population | - Support for the strengthening of community identity | - Participatory development of community projects. | 2 Community projects | Community project Meeting Registration Training Record audiovisual materials | IFC Performance Standard No. 1:Assessment and management of environmental and social risks and impacts Equator Principles No. 5: Participation of the Interest Groups ISO26000: Community SDG 1: End of Poverty SDG 11: Sustainable Cities and Communities SDG2: Zero Hunger |
| ADA and AID population |  | - Enabling a Community Center in coordination with local governments and the community. | A community center enabled | Meeting Registration audiovisual materials |  |
| ADA and AID population | - Support for the strengthening of community organizations in the area | - Coordinate technical assistance for producer committees. | No. of technical assistance granted | Training Record |  |
| ADA and AID Population / Interest Group (Private Sector). |  | - Generate spaces to connect supply and demand (small producers with large organizations). | No. of connections achieved | Audiovisual material Contracts Meeting Registration |  |
| ADA, AID and AII Population / General Population | - Promotion and development of Local Tourism | - [Continuity of actions] in alliance with the National Secretary of Tourism and local governments. | [Number of actions carried out] | [Reports] | IFC Performance Standard No. 1:Assessment and management of environmental and social risks and impacts Equator Principles No. 5:Participation of the Interest Groups ISO26000: Community SDG 1: End of Poverty SDG 11:Sustainable Cities and Communities |
| ADA, AID and AII Population / General Population |  | - Prepare a plan to contribute to the development and strengthening of local tourism. | No. of shares | Plan [Meeting minutes] |  |
| Inhabitants of the ADA and the AID | - Improvement of existing infrastructure and investment in new infrastructure. | - Mapping of public spaces such as squares, parks, courts, bus stops that require improvements in coordination with local governments. | N° of mapped spaces | Map of public spaces. | IFC Performance Standard No. 1:Assessment and management of environmental and social risks and impacts IFC Performance Standard #7:Indigenous villages Equator Principles No. 5:Participation of the Interest Groups ISO26000: Community SDG 1: End of Poverty SDG 11: Sustainable Cities and Communities |
| Inhabitants of the ADA and the AID |  | - Selection and improvement of public spaces. | 3 spaces selected | Photographic material |  |
| indigenous communities |  | - Generate spaces to connect supply and demand (small producers with large organizations). | No. of wells built | Audiovisual material Contracts Meeting Registration |  |
| indigenous communities |  | - Assistance for the construction of toilets in indigenous communities. | Number of toilets built | Photographic Records Contracts |  |
| indigenous communities | - Strengthening of family production and generation of added value. | - Provide agricultural technical assistance with competent professionals who effectively transfer methodologies and tools to families that allow them to increase their production capacities. | No. of technical assistance Number of people assisted | Training Record Audiovisual material | Equator Principles No. 5: Participation of the Interest Groups ISO26000: Community SDG 1: End of Poverty IFC Performance Standard #7: Indigenous villages SDG2: Zero Hunger |
| indigenous communities |  | - Training plan in innovation and value addition for those indigenous families that have the potential and desire to improve their products. | Number of training hours No. of people trained Products with higher added value generated | Training Record List of value-added products Audiovisual material |  |
| indigenous communities | - sustainable forest management | - Assist indigenous communities in the preparation and implementation of forest management plans that allow the correct use of this ecosystem service in a sustainable manner. | Number of training hours No. of people trained No. of plans developed | Training Record plans | Equator Principles No. 5: Participation of the Interest Groups ISO26000: Community SDG 15:Terrestrial Ecosystem Life IFC Performance Standard #7: Indigenous villages |

5.3. Schedule

| ACTIVITIES | [2022] |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Jan | Feb | March | Apr | may | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| - Participatory development of community projects (applies to the ADA). |  |  |  |  |  |  |  |  |  |  |  |  |
| - Enabling a Community Center in coordination with local governments and the community. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Coordinate technical assistance for producer committees. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Generate spaces to connect supply and demand (small producers with large organizations). |  |  |  |  |  |  |  |  |  |  |  |  |
| - [Continuity of actions] in alliance with the National Secretary of Tourism and local governments. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Prepare a plan to contribute to the development and strengthening of local tourism. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Mapping of public spaces such as squares, parks, courts, bus stops that require improvements in coordination with local governments. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Selection and improvement of public spaces. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Investments for the construction of drinking water wells in those indigenous communities that require it. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Assistance for the construction of toilets in indigenous communities. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Provide agricultural technical assistance with competent professionals who effectively transfer methodologies and tools to families that allow them to increase their production capacities. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Training plan in innovation and value addition for those indigenous families that have the potential and desire to improve their products. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Assist indigenous communities in the preparation and implementation of forest management plans that allow the correct use of this ecosystem service in a sustainable manner. |  |  |  |  |  |  |  |  |  |  |  |  |

Note: Schedules will be reviewed annually.

- BUDGET

| Assigned Budget | ----------------------------------------------- |
| --- | --- |

# REFERENCE DOCUMENTS

# ISO26000

# Sustainable Development Goals

# FSC standard

# IFC Performance Standards

# Social Study of the Forestry Component

# Social Study of the Industrial Component

# Study of the Indigenous Component

# RECORDS AND/OR ANNEX

# Community project

# [Meeting minutes]

# [Reports]

# Training Record

# audiovisual materials

# Contracts

# Agreement

# plans

# Map of public spaces.

# Photographic Records

# List of value-added products

# Linkage Policy with Indigenous Peoples

Clarification: In this document, the generic masculine terminology was adopted to refer to men and women alike. This is a resource that only seeks to give uniformity, simplicity and fluidity to the composition and reading of the text. It does not diminish, in any way, the commitment with which Paracel SA addresses gender equality.