| PRODUCED BY |  | REVIEWED BY | APPROVED BY |
| --- | --- | --- | --- |
| Noelia mendoza |  | Latifi Chelala | Latifi Chelala |
| Historical Reviews |  |  |  |
| Version | Date | Modifications |  |
| 00 | 12/01/2021 | Creation |  |
| 01 | 14/04/2021 | Page: All |  |

- [OBJECTIVES

Monitor the implementation of the measures and programs established in the PGS through the definition and monitoring of performance indicators, so that inconveniences in meeting the objectives set can be identified in time, and allow corrective actions to be taken in a manner timely. This program also contains a subcomponent for monitoring social perception through which it will be possible to have updated information regarding opinions and expectations of the local population on aspects related to the project in its different stages.

- SCOPE

The Social Monitoring program has the following scope:

| Place of Application | Industrial Component: Directly Affected Area (ADA), Area of ​​Direct Influence (AID). Forest Component: Area of ​​Indirect Influence (AID) Indigenous Communities: Redención, Jeguahaty, Vy'a Renda, Takuarendyju, Takuarita, Sati, Guyra Ñe'engatu Amba, Mberyvo. Yvyty Rovi, Apyka Jegua. |  |
| --- | --- | --- |
| Components | Industrial | Forest |
| Stages | Design, construction and operation. | Installation, operation and maintenance. |

- DEFINITIONS

- Area of ​​Direct Influence (AID) of the industrial component: They include 4 districts near the site of the Industrial Plant, including 18 communities that are within a radius of 13 km from the site. These territories are the following: Concepción, Belén, Horqueta and Loreto, and the communities/localities: L. Petit, Cnel. Mongelós, Jhugua Zarzo, Laguna Plato, Mongelós Pirity, Piquete Cue, Jhugua Gonzalez, Callejón San Luis, Mbocayaty, Callejón San Ramón, San Antonio, Curuzu Ñu, Costa Pucu, Paso Ita, Ko'ê Porâ, Costa Ferreira, Saladillo and Colonia Primavera.

- Area of ​​Direct Influence (AID) of the forestry component: It includes 7 districts in which the areas of the project's forest plantations and the main access roads to them are located, including 16 neighboring communities. These territories are the following: Sargento José Félix López, Paso Barreto, Loreto, San Alfredo, Horqueta and Arroyito of the department of Concepción; the Bella Vista Norte district of the Amambay department and its communities / localities: Isla Hermosa (Isla Tuyú), locality of Paso Barreto, Colonia Jorge Sebastián Miranda (Jhugua Ñandu), Estribo del Plata, Puentesiño, Laguna Cristo Rey, Anderi, Islería , Virgen del Camino, Jhugua Guasu, Jhugua Po'i, Santísima Trinidad, Paso Mbutu, Calle 15, Dominguez Nigó, and Ayala Cué.

- Directly Affected Area (ADA) of the industrial component: Social units and communities located in the immediate surroundings of the Industrial Plant installation, within a radius of 1 km. It includes a micro-territory called Piquete Cue.

- Area of ​​Direct Influence (AID) of the indigenous component: It is made up of indigenous communities located between 1 to 15 kilometers from Paracel SA's ventures and that could be affected by the project. The indigenous communities identified are from the Paĩ Tavyterã and Mbya Guaraní ethnic groups and a multicultural indigenous community made up of indigenous people of different ethnicities, mainly from the Maskoy language. The indigenous communities identified are: Redención, Jeguahaty, Vy'a Renda, Takuarendyju, Takuarita, Sati, Guyra Ñe'engatu Amba, Mberyvo, Yvyty Rovi, Apyka Jegua.

- Interest groups: People or groups of people who have an impact on (or are affected by) the activities, products or services of the company. These people or groups of people can have a direct or indirect influence on the image, reputation, decisions and actions of Paracel SA. In this document they are also called public of interest or interested parties.

- RESPONSIBILITIES

| Communications and Social Sustainability Management | Design the social intervention strategies framed in this program and lead their implementation. |
| --- | --- |
| All areas of the company | Comply with the provisions of this program (if applicable). |
| General management | Approve budgets for the program. |

- DEVELOPMENT

5.1 Related Impacts

to. Industrial and Forestry Components:

- Generation of expectations and fears in the local population.

- Generation of expectations at the regional and extra-regional level.

- Changes in customs and uses.

- Impact on ecosystem services.

- Possible impact on means of subsistence and / or the local economy.

b. Indigenous Component

- Quality of life, uses and customs.

- Work and working conditions.

- Social organization and own political institutions.

- Community health and safety.

- Use of ecosystem services related to livelihoods.

- Gender equality].

5.2 Development of Proposed Measures

| [Associated Population] | Proposed Measures | Concrete actions | Indicators | Methods of verification | Linked norms and / or standards |
| --- | --- | --- | --- | --- | --- |
| N / A | - Definition of measurement instruments for the implementation of activities. | - Preparation of an impact measurement instructions. | Number of impact assessment methods used | Impact Measurement Instructions | IFC Performance Standards No. 1: Evaluation and management of environmental and social risks and impacts Equator Principle No. 5: Stakeholder Participation Equator Principle N ° 4: Environmental and Social Management System and Action Plan |
| N / A |  | - Establish follow-up and review meetings of the actions and indicators established in the social programs. | No. of meetings | Meeting notes Records Updating of social programs |  |
| N / A |  | - Identify the activities of the programs that require corrective actions, improvements or rectification. | No. of activities identified No. of improvements applied | Meeting notes Reports Records Updating of social programs |  |
| ADA and AID Communities / Indigenous Communities | - [Monitoring of social perception] | - Collect information on the perceptions of the population, referents and local authorities, on the progress of the project (workshops, focus groups, interviews, etc.). | No. meetings No. of people reached No. of registered earnings | Meeting notes Social Perception Report Attendance Record |  |
| Indigenous Communities |  | - [Monitor compliance with agreements through semiannual meetings with indigenous communities, with the support of an outsourced institution]. | [No. of meetings] | [Record of meeting] | [IFC Performance Standards No. 7: Indigenous villages]. |
| Indigenous Communities |  | - [Hold semiannual meetings to monitor joint work with the Paraguayan Indigenous Institute (INDI)] | [No. of meetings] | [Record of meeting] |  |

5.3. Schedule

| ACTIVITIES | 2021 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| - Preparation of an impact measurement instructions. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Establish follow-up and review meetings of the actions and indicators established in the social programs. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Identify the activities of the programs that require corrective actions, improvements or rectification. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Collect information on the perceptions of the population, referents and local authorities, on the progress of the project (workshops, focus groups, interviews, etc.). |  |  |  |  |  |  |  |  |  |  |  |  |
| - [Monitor compliance with agreements through semiannual meetings with indigenous communities, with the support of an outsourced institution.] |  |  |  |  |  |  |  |  |  |  |  |  |
| - [Hold semiannual meetings to monitor joint work with the Paraguayan Indigenous Institute (INDI)]. |  |  |  |  |  |  |  |  |  |  |  |  |

Observation: The schedules will be reviewed annually.

- [BUDGET]

| Budget Assigned | ----------------------------------------------- |
| --- | --- |

- [REFERENCE DOCUMENTS

Social Study of the Industrial Component

Social Study of the Forest Component

Social Study of the Indigenous Component

ISO 26000

Sustainable Development Goals

FSC standard

IFC Performance Standards]

- [RECORDS AND / OR ANNEX

Impact Measurement Instructions

Meeting notes

Social Programs Update Registry

Reports

Meeting notes

Attendance Record

Record of meeting]

Clarification: In this document the generic masculine terminology was adopted to refer to men and women equally. This is a resource that only seeks to give uniformity, simplicity and fluidity to the composition and reading of the text. It does not diminish, in any way, the commitment with which Paracel SA addresses gender equality.