| PRODUCED BY |  | REVIEWED BY | APPROVED BY |
| --- | --- | --- | --- |
| Noelia Mendoza |  | Latifi Chelala | Latifi Chelala |
| Historical Reviews |  |  |  |
| Version | Date | Modifications |  |
| 00 | 24/05/2021 | Creation |  |

- OBJECTIVES

Empowering indigenous women to bridge gender and ethnic inequality gaps.

- SCOPE

The Women's Empowerment program has the following scope:

| Place of Application | Indigenous Communities: Redención, Jeguahaty, Vy'a Renda, Takuarendyju, Takuarita, Sati, Guyra Ñe'engatu Amba, Mberyvo. Yvyty Rovi, Apyka Jegua. |  |
| --- | --- | --- |
| Components | Industrial | Forest |
| Stages | Construction and operation | Installation, operation and maintenance |

- DEFINITIONS

- Area of ​​Direct Influence (AID) of the indigenous component: It is made up of indigenous communities located between 1 to 15 kilometers from Paracel SA's ventures and that could be affected by the project. The indigenous communities identified are from the Paĩ Tavyterã and Mbya Guaraní ethnic groups and a multicultural indigenous community made up of indigenous people of different ethnicities, mainly from the Maskoy language. The indigenous communities identified are: Redención, Jeguahaty, Vy'a Renda, Takuarendyju, Takuarita, Sati, Guyra Ñe'engatu Amba, Mberyvo, Yvyty Rovi, Apyka Jegua.

- RESPONSIBILITIES

| Communications and Social Sustainability Management | Design the social intervention strategies framed in this program and lead their implementation. |
| --- | --- |
| Human Talent Area | Support and implement the strategies and actions framed in this program. |
| General Management | Approve budgets for the program. |

- DEVELOPMENT

5.1. Related Impacts

a. Indigenous Component

- Strengthening the role of women in the social structure thanks to education and work.

- Participation in strategies of visibility and improvement of gender equality.

- Increased opportunities for professional training.

5.2. Development of Proposed Measures

| Associated Population | Proposed Measures | Concrete actions | Indicators | Methods of verification | Linked norms and / or standards |
| --- | --- | --- | --- | --- | --- |
| Indigenous Communities | - Promote gender equality and empower all women and girls. | - Carry out awareness workshops on the situation of indigenous women, as well as on women's rights, agreements and laws that promote gender equality. | No. of Workshops Developed No. of Participating People (age classification) | Training Record Materials used Photographic Records | IFC Performance Standard # 1: Evaluation and management of environmental and social risks and impacts ISO 26000: Human rights SDG 5: Gender equality IFC Performance Standards No. 7: Indigenous villages. |
|  |  | - Disseminate public programs that aim at gender equality, the prevention of violence in all its forms and the containment of victims. | No. of broadcast programs | Graphic pieces used |  |
|  |  | - Implement leadership training programs specifically for indigenous women. | No. of trainings given No. of Participating People (age classification) | Training Record Materials used Photographic Records |  |
|  |  | - Promote the inclusion and hiring of indigenous women in Paracel's value chain. | No. of indigenous women hired | Contract |  |
|  |  | - Promote the purchase of products and services made by indigenous women entrepreneurs. | No. of women benefited No. of products sold | Trade agreements |  |
|  |  | - Establish support and dialogue groups for indigenous families. | No. of sessions No. of families involved (classification by age and sex) | Session Registration |  |
|  |  | - Establish a committee of indigenous women. | No. of participating women (age classification) | Meeting Record Committee Constitution Act |  |

Observation: The schedules will be reviewed annually.

5.3. Schedule

| ACTIVITIES | 2021 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Jan | Feb | March | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| - Carry out awareness workshops on the situation of indigenous women, women's rights and the agreements and laws that promote gender equality. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Disseminate public programs that aim at gender equality, the prevention of violence in all its forms and the containment of victims. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Implement specific leadership training programs for indigenous women. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Promote the inclusion and hiring of indigenous women in the value chain. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Promote the purchase of products and services made by indigenous women entrepreneurs. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Establish support and dialogue groups for indigenous families. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Establish a committee of indigenous women. |  |  |  |  |  |  |  |  |  |  |  |  |

- BUDGET

| Budget Assigned | ----------------------------------------------- |
| --- | --- |

- REFERENCE DOCUMENTS

Social Study of the Indigenous Component

ISO 26000

Sustainable Development Goals

FSC Standard

IFC Performance Standards

- RECORDS AND / OR ANNEX

Training Record

Photographic Records

Graphic pieces used

Contract

Trade agreements

Session Registration

Meeting Record

Committee Constitution Act

Clarification: In this document the generic masculine terminology was adopted to refer to men and women equally. This is a resource that only seeks to give uniformity, simplicity and fluidity to the composition and reading of the text. It does not diminish, in any way, the commitment with which Paracel SA addresses gender equality.